## Tabelle1
Digitalisation of Business Processes (DigiBP) |  |  |  |  | 2019
|  | Lead Role | Time | Task Deadline | October |  |  |  | November |  |  |  | December
[5 empty] | KW40 | KW41 | KW42 | KW43 | KW44 | KW45 | KW46 | KW47 | KW48 | KW49 | KW50 | KW51
Milestone 1
Description of use case |  | All |  | 2019-10-17 | bar: October KW40 to October KW42
Creation of high level project plan |  | All |  | 2019-10-17 | bar: October KW40 to October KW42
Creation of strategic process model |  | All |  | 2019-10-17 | bar: October KW40 to October KW42
Feedback Milstone 1 |  | Coach |  | 2019-10-24 | bar: October KW43
Include feedback on Milestone 1 |  | All |  | 2019-10-31 | bar: November KW44
Milestone 2
Operational process model (to-be) including service task and decision tasks |  | All |  | 2019-11-07 | bar: November KW44 to November KW45
Project Plan with Team Roles |  | All |  | 2019-11-07 | bar: November KW44 to November KW45
Feedback Milstone 2 |  | Coach |  | 2019-11-14 | bar: November KW46
Include feedback on Milestone 2 |  | All |  | 2019-11-21 | bar: November KW47
Milestone 3
Intelligen Process Model including AI tasks |  | All |  | 2019-11-28 | bar: November KW47 to December KW48
Markdown documentation of the use case |  | All |  | 2019-11-28 | bar: November KW47 to December KW48
Feedback Milstone 3 |  | Coach |  | 2019-12-05 | bar: December KW49
Final presentation and submission of project |  | All |  | 2019-12-19 | bar: December KW50
[5 empty] | KW40 | KW41 | KW42 | KW43 | KW44 | KW45 | KW46 | KW47 | KW48 | KW49 | KW50 | KW51
[5 empty] | October |  |  |  | November |  |  |  | December
2019
| FHNW |  |  |  | KW43: Teamwork; KW47: Coach; KW50: Milestone
CalendarWeeks = KW
http://kalenderwoche.net/alle-kalenderwochen-2019.php
Team Roles
Sebastian Kluthe
Teyfik Agac
Pamela Streisguth